## Slide 1: The ‘EU – Balkan countries Action Plan in S&T’: Achievements, weaknesses and ways forward
Dr. George BONAS
General Secretariat for Research and Technology (GSRT)

## Slide 2: The Action Plan
Adopted WBC, EU-MS, C.C., EC at Ministerial level in 2003
Main fields of intervention:
  Renewal of infrastructures;
  Improvement of Human Potential;
  Institution building;
  Joint RTD activities
Duration 3 years; No specific budget

## Slide 3: The Action Plan: Achievements
Strong momentum in S&T cooperation
Policy oriented initiatives (SEE-ERA.NET project, Steering Platform, etc.)
Specific calls in FP6 (Capacity building, joint RTD, etc.)
Several projects on e-infrastructures (SEEREN, SINSEE, SEE-Grid, etc.)

## Slide 4: The Action Plan: weaknesses
Limited progress on two key issues for the integration of WBC in ERA:
  Improvement of infra-structures;
  Restructuring of S&T systems
Main reason: limited and inadequate sources of funding (FP6, Interreg, NATO) and, in particular, no support from CARDS

## Slide 5: What went ‘wrong’ with CARDS?
Different ‘decision making groups’:
  DG RTD, Ministries for Research (EU + WBC)
  DG Relex, Ministries of Foreign Affairs (EU), Ministries of Finance (WBC)
Different programming periods:
  CARDS: 2002 – 2006
  Action Plan: 2003 - 2006

## Slide 6: Current environment and ways forward
Integration of WBC in ERA
Instrument for Pre-Accession (IPA)
FP7 for RTD
Res. Infra
Restructuring S&T systems
Joint RTD
Mobility

## Slide 7: To be successful: coordination at 3 levels
European Commission
  DG RTD; DG Enlargement
EU Member States
  Ministries for Research; Ministries ‘for IPA’
Last but not least: WBC
  Sound proposals from Ministries for Research to Ministries of Finance, which finalize the list of National priorities

## Slide 8: Conclusion
The stakeholders are aware of the need to support S&T for the integration in ERA and as a tool for economic growth
New instruments will be in place in few months
… Can we be optimistic?
Thank you for your attention!